## Sheet1
Name | Application | Page | Edit Type | Priority | Issue | Date Added | Assignee | Pushed | Approved | Notes
Axel | Android | sign-up | UI | High | Format fields such as phone number( (XXX) XXX-XXXX, CC number (XXXX XXXX XXXX XXXX) | 2018-10-21 | Alex | FALSE | FALSE
Axel | Android | sign-up -> facial | UI | Medium | Make pop-up messages look better | 2018-10-21 | Alex | FALSE | FALSE
Axel | Android | settings | UI | High | Group items on settings page similar to settings page | 2018-10-21 | Alex | FALSE | FALSE
Marsol | Android | Transaction | UI | Critical | Redesign of Transaction pages (buyer/seller) | 2018-10-23 | Alex | TRUE | FALSE
Axel | Android | Home, Transaction | functionality | Critical | Change text to cards on listview (info on card: price (in correct color), buyer/seller, note, status) | 2018-11-08 | Alex | FALSE | FALSE
Axel | Android | home | UI | Low | Change color of settings button | 2018-10-21 | Alex | TRUE | TRUE |  | lalingeman@oakland.edu
Axel | Android | sign-up -> all pages | UI | Medium | Center next button, change look of next button | 2018-10-21 | Alex | TRUE | TRUE |  | acalandra@oakland.edu
Axel | Android | sign-in | Content, UI | Medium | Change the amazon logo to paytel logo, clean-up this page | 2018-10-21 | Alex | TRUE | TRUE |  | apdapoz@oakland.edu
Axel | Android | settings | UI | Low | Format fields such as phone number( (XXX) XXX-XXXX, CC number (XXXX XXXX XXXX XXXX) | 2018-10-21 | Alex | TRUE | TRUE
Axel | Android | sign-up -> payment | UI | High | exp-date auto add / | 2018-10-21 | Alex, anthony | FALSE | FALSE
Axel | Android | sign-up -> address | UI, functionality | Low | Change state input field to dropdown menu | 2018-10-21 | Alex, Anthony | FALSE | FALSE
Axel | Android | settings | UI | Medium | exp-date auto add / | 2018-10-21 | Alex, anthony | TRUE | TRUE
Axel | Android | sign-up -> identity | functionality | Critical | integrate username check into exisiting checks | 2018-10-21 | Anthony | TRUE | FALSE | In authentication_signup_identity you can find a function checkusername() to query the db for the username. This function is working and has to be integrated into the existing checks. I commented in the check_username() function where it decides if it is unique or not with a system.out.println(). If you have questions let me know
Marsol | Android | add Funds to Wallet | functionality | Medium | Add Checks for Wallet add | 2018-11-03 | Anthony | TRUE | FALSE
Axel | Android | Transaction -> seller | functionality | Critical | Add button lock for 30 seconds with dialogue | 2018-11-08 | Anthony
Axel | Android | sign-up -> payment | functionality | Critical | Check that month(1-12) and year are valid(>18) | 2018-10-21 | Anthony | TRUE | TRUE
Axel | Backend | authentication | functionality | High | Integrate facial expressions | 2018-10-21 | Axel | FALSE | FALSE
Axel | Android | Transaction -> seller flow | UI | High | Show api feedback | 2018-11-08 | Axel | FALSE | FALSE
Axel | Backend | authentication | functionality | Low | change facial library from global to user attached library | 2018-10-21 | Axel | TRUE | TRUE
Axel | Android | everywhere with api call | UI | High | Show api feedback to user | 2018-11-05 | Axel, Lauren | TRUE | FALSE
Axel | Android | Home | UI, functionality | Medium | Add sign out button | 2018-11-08 | Axel, Marsol
Axel | Documentation | ALL |  | Low | documentation | 2018-11-08 | EVERYONE
Axel | Presentation | ALL |  | Low | Presentation | 2018-11-08 | EVERYONE
Axel | Android | Home, Transaction | functionality | Critical | Split up transaction list (pending -> home, others -> transaction) | 2018-11-08 | Marsol | FALSE | FALSE
Axel | Android | Transaction -> buyer flow | functionality | Medium | Add fingerprint to facial rekognition page | 2018-11-08 | Marsol | FALSE | FALSE
Axel | Android | Transaction approval | functionality | Critical | I am getting an error sometimes when the home page opens, see notes image | 10/230/2018 | Marsol | TRUE | TRUE
Axel | Android | sign-up -> identity | functionality | High | query username for unique | 2018-10-21 | Marsol, Axel | TRUE | TRUE |  | nmmcgivern@oakland.edu
Axel | webApp | Transaction table | UI | High | Show note in table | 2018-11-08 | Noah | TRUE
Axel | webApp | User Tabel | UI | High | Hide user id in table, show username instead | 2018-11-08 | Noah | TRUE
Axel | webApp | clean up css | UI | High | Table css properties | 2018-11-08 | Noah
Axel | webApp | User info page | UI, functionality | Medium | Show user transactions in table | 2018-11-08 | Noah
Axel | webApp | User info page | functionality | Medium | Change from user id to username | 2018-11-08 | Noah | TRUE
[8 empty] | FALSE | FALSE
Completed
High
High
Critical
High
Medium
High
High
Critical
Critical
Critical
Critical
Medium
High
High
Critical
Critical