## Sheet1
Name | Application | Page | Edit Type | Priority | Issue | Date Added | Assignee | Pushed | Approved | Notes
Axel | Android | Transaction -> buyer flow | functionality | Critical | Add fingerprint to facial rekognition page | 2018-11-08 | Marsol | TRUE | TRUE
Axel | Android | ALL | TEST | High | Write test cases | 2018-11-15 | Anthony | FALSE
Axel | Android | Home | UI, functionality | Critical | Add sign out button on top left page (Marsol or Axel will add functionality | 2018-11-18 | Alex
Marsol | Android | Home | Functionality | Critical | Add Timeout for spamming buttons | 2018-11-27 | Marsol | TRUE | TRUE
Axel | Android | Seller transaction | functionality | Critical | Do username check here and make sure it is not the current user's username | 2018-11-25 | Anthony
Axel | Android | Transaction | UI | Critical | Format imageView for users | 2018-11-28 | Alex | TRUE | FALSE
Axel | Android | Transaction -> seller | functionality | Critical | Amount should be > 1 | 2018-11-28 | Anthony |  | FALSE
Axel | Android | Transaction view | UI | Critical | Rotate image | 2018-11-29 | Alex
Axel | webApp | Transaction | UI, functionality | Critical | Show images from s3 transactions | 2018-11-15 | Noah | FALSE | FALSE
Axel | Presentation |  |  | Critical | Make presentation similar looking to app | 2018-11-29 | Alex
Axel | Documentation | ALL |  | High | documentation | 2018-11-08 | EVERYONE
[5 empty] | On-screen Appearance of landing and other pages requirements |  | Alex
[5 empty] | Wireframe designs |  | Alex
[5 empty] | User Interface Specifications:Preliminary Design |  | Alex
[5 empty] | System Operation Contracts |  | Marsol
[5 empty] | Mathematical Model |  | Marsol
[5 empty] | Dynamic Design:Interface Specifications |  | Marsol
[5 empty] | State Diagrams |  | Lauren
Mapping Subsystems to Hardware (Deployment Diagram)
[5 empty] | Network Protocol |  | Noah
[5 empty] | Global Control Flow |  | Noah
Algorithms and Data Structures
[5 empty] | User Interface Design and Implementation |  | Alex
[5 empty] | Testing |  | Anthony
[5 empty] | Project Management |  | Lauren
[5 empty] | References |  | EVERYONE
Axel | Presentation | ALL |  | High | Presentation | 2018-11-08 | EVERYONE
Axel | Presenation | ALL |  | Low | Poster board | 2018-11-19 | EVERYONE
[8 empty] | FALSE | FALSE
Completed
Axel | Android | sign-up -> identity | functionality | High | query username for unique | 2018-10-21 | Marsol, Axel | TRUE | TRUE |  | nmmcgivern@oakland.edu
Axel | Android | home | UI | Low | Change color of settings button | 2018-10-21 | Alex | TRUE | TRUE |  | lalingeman@oakland.edu
Axel | Android | sign-up -> all pages | UI | Medium | Center next button, change look of next button | 2018-10-21 | Alex | TRUE | TRUE |  | acalandra@oakland.edu
Axel | Android | sign-in | Content, UI | Medium | Change the amazon logo to paytel logo, clean-up this page | 2018-10-21 | Alex | TRUE | TRUE |  | apdapoz@oakland.edu
Axel | Android | Transaction approval | functionality | Critical | I am getting an error sometimes when the home page opens, see notes image | 10/230/2018 | Marsol | TRUE | TRUE
Axel | Backend | authentication | functionality | Low | change facial library from global to user attached library | 2018-10-21 | Axel | TRUE | TRUE
Axel | Android | sign-up -> payment | functionality | Critical | Check that month(1-12) and year are valid(>18) | 2018-10-21 | Anthony | TRUE | TRUE
Axel | Android | settings | UI | Low | Format fields such as phone number( (XXX) XXX-XXXX, CC number (XXXX XXXX XXXX XXXX) | 2018-10-21 | Alex | TRUE | TRUE
Axel | Android | settings | UI | Medium | exp-date auto add / | 2018-10-21 | Alex, anthony | TRUE | TRUE
Axel | Android | sign-up | UI | High | Format fields such as phone number( (XXX) XXX-XXXX, CC number (XXXX XXXX XXXX XXXX) | 2018-10-21 | Alex | TRUE | TRUE
Axel | Android | sign-up -> payment | UI | High | exp-date auto add / | 2018-10-21 | Alex, anthony | TRUE | TRUE
Axel | Android | sign-up -> address | UI, functionality | Low | Change state input field to dropdown menu | 2018-10-21 | Alex, Anthony | TRUE | TRUE
Axel | Android | sign-up -> facial | UI | Medium | Make pop-up messages look better | 2018-10-21 | Alex | TRUE | TRUE
Marsol | Android | add Funds to Wallet | functionality | Medium | Add Checks for Wallet add | 2018-11-03 | Anthony | TRUE | TRUE
Axel | Android | everywhere with api call | UI | High | Show api feedback to user | 2018-11-05 | Axel, Lauren | TRUE | TRUE
Axel | Android | Home, Transaction | functionality | Critical | Split up transaction list (pending -> home, others -> transaction) | 2018-11-08 | Marsol | TRUE | TRUE
Axel | Android | Home, Transaction | functionality | Critical | Change text to cards on listview (info on card: price (in correct color), buyer/seller, note, status) | 2018-11-08 | Alex | TRUE | TRUE
Axel | Android | Transaction -> seller | functionality | Critical | Add button lock for 30 seconds with dialogue | 2018-11-08 | Anthony | TRUE | TRUE
Axel | webApp | Transaction table | UI | High | Show note in table | 2018-11-08 | Noah | TRUE | TRUE
Axel | webApp | User Tabel | UI | High | Hide user id in table, show username instead | 2018-11-08 | Noah | TRUE | TRUE
Axel | webApp | User info page | UI, functionality | Medium | Show user transactions in table | 2018-11-08 | Noah | TRUE | TRUE
Axel | webApp | User info page | functionality | Medium | Change from user id to username | 2018-11-08 | Noah | TRUE | TRUE
Axel | Android | Home | UI | Critical | Strectch home bar over full width | 2018-11-15 | Axel | TRUE | TRUE
Axel | Android | Transaction -> seller flow | UI | High | Show api feedback | 2018-11-08 | Axel | TRUE | TRUE
Axel | Android | Home | UI, functionality | High | Add sign out button | 2018-11-08 | Axel, Marsol | TRUE | TRUE
Axel | Android | Sign-up -> Address | UI | High | Zip code 5 numbers | 2018-11-15 | Alex | TRUE | TRUE
Axel | Android | Wallet | UI | High | Add funds has to have number keyboard | 2018-11-15 | Axel | TRUE | TRUE
Axel | Android | ALL | functionality | High | Disable back button on some places | 2018-11-15 | Axel | TRUE | TRUE
Axel | webApp | Transaction | UI, functionality | High | Save images associated with transaction | 2018-11-15 | Axel | TRUE | TRUE
Axel | Android | settings | UI | High | Group items on settings page similar to sign up flow | 2018-10-21 | Alex | TRUE | TRUE
Axel | Android | Sign up ->payment | functionality | High | CVC max of 3 characters | 2018-11-18 | Axel | TRUE | TRUE
Axel | Android | authentication | functionality | High | Integrate facial expressions | 2018-10-21 | Axel | TRUE | TRUE
Axel | Android | Buyer->approve | functionality | Critical | Check wallet balance | 2018-11-15 | Anthony | TRUE | TRUE
Anthony | Andriod | Sign Up Identity | UI, Functionality | Critical | Fix Phone Number Check to fit new UI layout | 2018-11-24 | Anthony | TRUE | TRUE
Axel | Android | Home page | functionality | Critical | Wallet amount doesn't load properly | 2018-11-18 | Marsol | TRUE | TRUE
Axel | Android | sign-up -> identity | functionality | Critical | integrate username check into exisiting checks | 2018-10-21 | Anthony | TRUE | TRUE
Marsol | Android | Transaction | UI | Critical | Redesign of Transaction pages (buyer/seller) | 2018-10-23 | Alex | TRUE | TRUE
Marsol | Android | Home | UI, functionality | High | Set invisible Text field for $$ and put user | 2018-11-18 | Marsol | TRUE | TRUE
Axel | Android | ALL | functionality | Critical | Username check needs to compare lowercase version | 2018-11-24 | Anthony | TRUE | TRUE
Axel | Android | Sign up ->first page | UI | Critical | Username already taken shows when the username doesn't exist yet. I can click on next and it will take me to the next page. | 2018-11-24 | Anthony | TRUE | TRUE
Axel | T-Shirt |  |  | Critical | BUY T-SHIRTS | 2018-11-15 | Anthony | TRUE | TRUE | Should be in Matt Bruer's office will retreive them Monday
Axel | Android | Sign up -> complete | UI | Critical | Center text and make logo smaller | 2018-11-24 | Alex | TRUE | TRUE
Axel | Android | View transaction | UI | Critical | Clean up text on top(bigger) and correct color for amount | 2018-11-24 | Alex | TRUE | TRUE
Axel | webApp | clean up css | UI | Critical | Table css properties | 2018-11-08 | Noah | TRUE | TRUE
High
High
Critical
High
Medium
High
High
Critical
Critical
Critical
Critical
Medium
High
High
Critical
Critical

## Anthony's Issues
Name | Application | Page | Edit Type | Priority | Issue | Date Added | Assignee
Axel | Android | ALL | TEST | High | Write test cases | 2018-11-15 | Anthony
Axel | Android | Seller transaction | functionality | Critical | Do username check here and make sure it is not the current user's username | 2018-11-25 | Anthony
Axel | Android | Transaction -> seller | functionality | Critical | Amount should be > 1 | 2018-11-28 | Anthony
Axel | Documentation | ALL |  | High | documentation | 2018-11-08 | EVERYONE
[5 empty] | Testing |  | Anthony